## Sheet1
AGILE PROJECT PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | Code, Report,Git Repository
| Vehicle dataset Analysis | Athanasios Staikopoulos | 2022-04-10 | 2022-04-23 |  | 100% |  | SCOPE STATEMENT | Perform Analysis on Customer and loan dataset.
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE |  | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
No | Sprint 1 |  | Ronu Skariah |  | 2022-04-10 | 2022-04-02 | 10
No | Dataset selection | Requirement Gathering | Ronu Skariah |  | 2022-04-10 | 2022-04-12 | 2 | completed | Selected the customer and loan dataset and gathered the data from kaggle. Created an account in Mockaroo to generate more data which are unstructured and created an API for it from Mockaroo.
No | Dataset Analysis | Requirement Analysis | Ronu Skariah |  | 2022-04-13 | 2022-04-14 | 1 | completed | In this task, the analysis of the problem statement along with various KPIs is required to solve the problem statements.
No | Infrastructure setup | Infrastructure | Ronu Skariah |  | 2022-04-15 | 2022-04-16 | 2 | completed | Setting up Spark in local. Installing Java 8 setting the spark home and java home environmental variables. Created an Azure VM and install MYSQL in it. Created Amazon S3 bucket.
No | Package installation and coding creation | Development | Ronu Skariah |  | 2022-04-15 | 2022-04-16 | 1 | completed | In this task got some error while trying to connect to Amazon s3, MYSQL,Spark and Mockaroo. Research was done to resolve it and it was resolved by install boto3 client for awss3, sqlalchemy for MYSQL, requests for making get/post request to an API and finally install pyspark and findspark in anaconda.
No | Coding - Establish and test connection with all cloud services from jupyter notebook | Development | Ronu Skariah |  | 2022-04-16 | 2022-04-17 | 1 | completed | This task includes to establish and test connection with S3, MYSQL and Mockaroo.
No | Code for Read data from API and CSV , perform preprocessing and storing in Database in Vm and NoSQL database | Development | Ronu Skariah |  | 2022-04-18 | 2022-04-19 | 1 | completed | All task includes : 1. Read data from Kaggle(structured) covert to pandas dataframe and read data from Mockaroo API (unstructured) convert into Spark Dataframe and later on pandas dataframe. 2. Combine DataFrame 3. Cleaning the data. 4. Visualize the null values and plotting box plot for checking the outliers 5. Storing data on S3. 6. Removing null values and Outliers 7. Storing the structured cleansed data into MYSQL in VM .
No | Coding - Perform Visualization | Development | Ronu Skariah |  | 2022-04-19 | 2022-04-20 | 1 | completed | Performed various visualization on the cleaned data and also create an interactive 3D plot using the plotly library.
No | Testing Code and Coding for Interactive Visualization | Test | Ronu Skariah |  | 2022-04-21 | 2022-04-22 | 1 | completed | In this task created a User Interactive part which takes data from the user and performs visualization on the filtered dataframe based on the data user has provided. Install the package tk '' pip install tk "
No | Report writing | Documentations | Ronu Skariah |  | 2022-04-22 | 2022-04-23 | 1 | completed | This taks include report writing for customer and loan dataset